## Sheet1
Task Name: (Dependencies top to bottom) | [7 empty] | Andrew Bellas | Jonathan Dang | Michael Do | Mohsin Shaik | Total
|  | Role | Owner | Estimated By Task | Effort Subtotals | Actual By Task | Actual By SubTotals | Actual | Actual | Actual | Actual
[8 empty] | By Task | By Task | By Task | By Task
| Information Gathering: |  |  |  | 2 |  | 5
Preliminary & Parallel Tasks | Creating preliminary questions to ask | Project Team | Team | 1 |  | 2 |  | 0.5 | 0.5 | 0.5 | 0.5 | 2
| Gather Information for Creation Connection Therapy | Project Team | (Michael,Andrew) | 1 |  | 3 |  | 1.5 |  | 1.5 |  | 3
| Readying Website Builder: |  |  |  | 2 |  | 6
| Installing wordpress and configure to sync data to GitHub | Developer | (Jon,Andrew) | 2 |  | 6 |  | 1 | 5 |  |  | 6
Design & Build Iteration 1: | Creation Connection Therapy Webpage Layout |  |  |  | 50 |  | 15
| About Page | Developer | Jon | 6 |  | 2 |  |  | 2 |  |  | 2
| Events Page | Developer | Mo | 6 |  | 0 | [5 empty] | 0
| FAQ Page | Developer | Michael | 5 |  | 3 |  |  |  | 3 |  | 3
| Contact Us Page | Developer | Jon | 6 |  | 3 |  |  | 3 |  |  | 3
| Getting Started Page | Developer | Mo | 5 |  | 0 | [5 empty] | 0
| Home Page | Developer | Andrew | 8 |  | 2 |  | 2 |  |  |  | 2
| Services Page | Developer | Michael | 6 |  | 3 |  |  |  | 3 |  | 3
| Website Header | Developer | Andrew | 8 |  | 2 |  | 2 |  |  |  | 2
Design, Content & Communication Iteration 2: | Creation Connection Therapy Content & Design |  |  |  | 38
| About Page | Developer | Jon | 6
| Events Page | Developer | Mo | 6
| FAQ Page | Developer | Michael | 5
| Contact Us Page | Developer | Jon | 5
| Getting Started Page | Developer | Mo | 5
| Home Page | Developer | Andrew | 2
| Services Page | Developer | Michael | 5
| Website Footer and Header | Developer | Team | 4
Total |  |  |  | 92 | 92 | 26 | 26 | 7 | 10.5 | 8 | 0.5 | 26